## Sheet1
# | Client | Assigned On | Age | Associate | SR # | Status | Sub-Status | Kanban Status | Followed on | Days | Summary | Last Followed mail
1 | ALBR_PA | 2021-05-17 | 30 | Jain O, Sonu | 436666291 | Pending | Client Validation | PROD_VALIDATION | 2021-06-14 | 2 | Add Locations to NRC Connect/Real Time Upload | Add Locations to NRC Connect/Real Time Upload
2 | ALBR_PA | 2021-05-25 | 22 | Jain O, Sonu | 437094496 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-16 | 0 | Admissions for CHF reporrt | Admissions for CHF reporrt
3 | ALBR_PA | 2021-05-25 | 22 | Jain O, Sonu | 436950516 | Planning In Progress |  | SCOPING | 2021-06-15 | 1 | Powerplan Usage report | Powerplan Usage report
4 | ALBR_PA | 2020-11-02 | 226 | Jain O, Sonu | 424854241 | Pending | Client Action Required | NON_PROD_VALIDATION | 2021-06-16 | 0 | Look into alternate methods of querying consulting physician for encounters | Look into alternate methods of querying consulting physician for encounters
5 | ALBR_PA | 2021-05-25 | 22 | Jain O, Sonu | 436515996 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Need to Revise the Uploads to NRC (move to Real Time survey for EMCP, EMCEP, Moss Rehab, Willowcrest | Need to Revise the Uploads to NRC (move to Real Time survey for EMCP, EMCEP, Moss Rehab, Willowcrest
6 | ALBR_PA | 2021-05-10 | 37 | Jain O, Sonu | 436805315 | Scheduled |  | PROD_READY | 2021-06-14 | 2 | Please create a data extract for the relationship of child birth to mom record. | Please create a data extract for the relationship of child birth to mom record.
7 | ALBR_PA | 2021-04-20 | 57 | Jain O, Sonu | 434351517 | Pending | Client Validation | PROD_VALIDATION | 2021-06-14 | 2 | Report from AeCIS | Report from AeCIS
8 | ALBR_PA | 2021-05-17 | 30 | Jain O, Sonu | 436634043 | Pending | Client Validation | PROD_VALIDATION | 2021-06-14 | 2 | Report needed in excel format | Report needed in excel format
9 | ALBR_PA | 2020-11-09 | 219 | Batheja, Srishti | 432417415 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-15 | 1 | Report add | Report add
10 | ALBR_PA | 2020-12-11 | 187 | Batheja, Srishti | 433713858 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-15 | 1 | Create new report for AMPAC Data | Create new report for AMPAC Data
11 | ALBR_PA | 2021-05-25 | 22 | Kumar S,Utham | 436294422 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Requesting a Cerner report | Requesting a Cerner report
12 | ALBR_PA | 2021-06-09 | 7 | Kumar S,Utham | 437031390 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-14 | 2 | she needs to run report with time frame to pull out gyn surgical cases | she needs to run report with time frame to pull out gyn surgical cases
13 | ALBR_PA | 2021-03-29 | 79 | Shree,D.Vipula | 435845185 | Pending | Client Validation | REVISION | 2021-06-14 | 2 | request for a patient report | request for a patient report
14 | ALBR_PA | 2021-04-22 | 55 | Shree,D.Vipula | 436204662 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-14 | 2 | User need Custom report build in cerner | User need Custom report build in cerner
15 | ALBR_PA | 2021-04-16 | 61 | Varun Ghanekar | 435587375 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Data Downloads | Data Downloads
16 | ALBR_PA | 2021-03-29 | 79 | Varun Ghanekar | 435845185 | Pending | Client Validation | REVISION | 2021-06-14 | 2 | request for a patient report | request for a patient report
17 | ALBR_PA | 2021-05-24 | 23 | Varun Ghanekar | 436951079 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | report Orders by Provider | report Orders by Provider
18 | ALBR_PA | 2021-04-22 | 55 | Varun Ghanekar | 436204662 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-14 | 2 | User need Custom report build in cerner | User need Custom report build in cerner
19 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 437169032 | Planning In Progress |  | BACKLOG | 2021-06-10 | 6 | Add column to report Appointment Extract File | Add column to report Appointment Extract File
20 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 437213062 | Planning In Progress |  | BACKLOG | 2021-06-14 | 2 | Copy Ambulatory Overdue Task Report but with editted criteria | Copy Ambulatory Overdue Task Report but with editted criteria
21 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 436929362 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-14 | 2 | Reports on volumes | Reports on volumes
22 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 437171719 | Planning In Progress |  | BACKLOG | 2021-06-14 | 2 | Create a custom report using the Confirmed appointment report in DA2 | Create a custom report using the Confirmed appointment report in DA2
23 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 429650975 | Planning In Progress |  | BACKLOG | 2021-06-10 | 6 | Make changes to aecis_rx_eprescribe | Make changes to aecis_rx_eprescribe
24 | ALBR_PA | N/A | 0 | Gangwar,Nidhi | 437053907 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-04 | 12 | Replace EBL DTA in Powerchart Maternity Census reporting in DA2 | Replace EBL DTA in Powerchart Maternity Census reporting in DA2
25 | BH_AL | 2021-03-01 | 107 | Jain O, Sonu | 435029900 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | NICU Central line count report | NICU Central line count report
26 | BH_AL | 2021-05-17 | 30 | Hinal Udeshi | 437096681 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-11 | 5 | EMRLink Radiology AOE Report | EMRLink Radiology AOE Report
27 | BH_AL | 2021-06-07 | 9 | Hinal Udeshi | 436527084 | Planning In Progress |  | CODING | 2021-06-15 | 1 | Transaction Data Medi-Centrix | Transaction Data Medi-Centrix
28 | BH_AL | 2021-05-17 | 30 | Hinal Udeshi | 437017734 | Planning In Progress |  | REVISION | 2021-06-15 | 1 | EMRLink Specimen Data | EMRLink Specimen Data
29 | BH_AL | 2021-05-11 | 36 | Hinal Udeshi | 437017719 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-11 | 5 | EMRLink Lab AOE Data | EMRLink Lab AOE Data
30 | BH_AL | 2021-03-14 | 94 | Hinal Udeshi | 434757498 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | Report Request from 12/9/20 Data Management Meeting - NICU Central Line Report | Report Request from 12/9/20 Data Management Meeting - NICU Central Line Report
31 | BH_AL | 2021-05-11 | 36 | Hinal Udeshi | 437017712 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-09 | 7 | EMRLink Lab Orders and Results | EMRLink Lab Orders and Results
32 | BH_AL | 2021-04-23 | 54 | Hinal Udeshi | 435975219 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Lab Culture Report | Lab Culture Report
33 | BH_AL | 2021-05-13 | 34 | Kumar S,Utham | 437035041 | Scheduled |  | PROD_VALIDATION | 2021-06-15 | 1 | EMRLink Radiology Orders | EMRLink Radiology Orders
34 | BH_AL | 2021-06-15 | 1 | Navya J | 436836120 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Invoice Level ATB - Medi-Centrix | Invoice Level ATB - Medi-Centrix
35 | BH_AL | 2021-06-03 | 13 | Navya J | 437264592 | Planning In Progress |  | CODING | 2021-06-15 | 1 | Bluesight Surginet Report | Bluesight Surginet Report
36 | BH_AL | 2021-06-06 | 10 | Navya J | 437450340 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | Physician Practices Patient Data | Physician Practices Patient Data
37 | BH_AL | 2021-04-26 | 51 | Navya J | 435992064 | Pending | Client Action Required | SCOPING | 2021-06-15 | 1 | Baptist Laboratory Outreach Monthly Volume | Baptist Laboratory Outreach Monthly Volume
38 | BH_AL | 2021-05-11 | 36 | Navya J | 436976816 | Planning In Progress |  | REVISION | 2021-06-15 | 1 | Daily Weights Report | Daily Weights Report
39 | BH_AL | 2021-05-03 | 44 | Navya J | 436172030 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-15 | 1 | Medi-Centrix - Demographics | Medi-Centrix - Demographics
40 | BH_AL | 2021-04-20 | 57 | Sharma,Sameer | 436351731 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-14 | 2 | Insurance Data Medi-Centrix | Insurance Data Medi-Centrix
41 | BH_AL | 2021-05-20 | 27 | Sharma,Sameer | 436163556 | Pending | Client Validation | PROD_VALIDATION | 2021-06-14 | 2 | Add assays to Discern Report | Add assays to Discern Report
42 | BH_AL | 2021-05-31 | 16 | Sharma,Sameer | 437264433 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Bluesight PowerChart Report | Bluesight PowerChart Report
43 | BH_AL | 2021-04-19 | 58 | Sharma,Sameer | 436352166 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Invoice Data Medi-Centrix | Invoice Data Medi-Centrix
44 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436812521 | Planning In Progress |  | BACKLOG | 2021-05-11 | 36 | Clinical Technology - Med Scanning | Clinical Technology - Med Scanning
45 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436566142 | Planning In Progress |  | BACKLOG | 2021-05-10 | 37 | Provider Message Center Audit | Provider Message Center Audit
46 | BH_AL | N/A | 0 | Gangwar,Nidhi | 437336873 | Planning In Progress |  | BACKLOG | 2021-05-31 | 16 | OUTPATIENT VISITS WITHIN LAST 72 HOURS | OUTPATIENT VISITS WITHIN LAST 72 HOURS
47 | BH_AL | N/A | 0 | Gangwar,Nidhi | 437217470 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-14 | 2 | Stroke List Report | Stroke List Report
48 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436812625 | Planning In Progress |  | BACKLOG | 2021-05-11 | 36 | Clinical Technology - Specimen Collection | Clinical Technology - Specimen Collection
49 | BH_AL | N/A | 0 | Gangwar,Nidhi | 437271065 | Planning In Progress |  | TRIAGE_REVIEW | 2021-05-26 | 21 | Historical CPA Data | Historical CPA Data
50 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436692821 | Planning In Progress |  | BACKLOG | 2021-05-10 | 37 | OR Efficiency Report | OR Efficiency Report
51 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436432787 | Planning In Progress |  | BACKLOG | 2021-05-10 | 37 | RT Task to POC BG complete Report request | RT Task to POC BG complete Report request
52 | BH_AL | N/A | 0 | Gangwar,Nidhi | 437577468 | Planning In Progress |  | BACKLOG | 2021-06-14 | 2 | CCM TCM Data Revision | CCM TCM Data Revision
53 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436439007 | Planning In Progress |  | BACKLOG | 2021-05-10 | 37 | BMCS BG TAT w Nancy's rule | BMCS BG TAT w Nancy's rule
54 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436613932 | Planning In Progress |  | BACKLOG | 2021-06-14 | 2 | Billed Charge Data Medi-Centrix | Billed Charge Data Medi-Centrix
55 | BH_AL | N/A | 0 | Gangwar,Nidhi | 436766856 | Planning In Progress |  | BACKLOG | 2021-06-07 | 9 | Missed Therapy | Missed Therapy
56 | BLTM_WI | 2021-06-08 | 8 | Chandan Sharma | 437480488 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Need "Attending Physician" added to Report Titled: Scheduled Patients Demographics Report" | Need "Attending Physician" added to Report Titled: Scheduled Patients Demographics Report"
57 | BLTM_WI | 2021-05-19 | 28 | Chandan Sharma | 437117819 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Modification to report titled "Scheduled Patients Demographics Report" | Modification to report titled "Scheduled Patients Demographics Report"
58 | BLTM_WI | 2021-06-02 | 14 | R,Sunitha | 437263364 | Scheduled For Approval |  | PROD_READY | 2021-06-14 | 2 | Update reports for portal appointment]confirm changes | Update reports for portal appointment]confirm changes
59 | BLTM_WI | 2021-06-08 | 8 | R,Sunitha | 437422825 | Scheduled For Approval |  | PROD_READY | 2021-06-16 | 0 | Report modification - bsc_scan_compliance | Report modification - bsc_scan_compliance
60 | BLTM_WI | 2021-05-10 | 37 | R,Sunitha | 436766874 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-11 | 5 | No Show report | No Show report
61 | BLTM_WI | 2021-03-03 | 105 | R,Sunitha | 435625165 | Planning In Progress |  | CODING | 2021-06-14 | 2 | FCC Optimizations - Reporting | FCC Optimizations - Reporting
62 | BLTM_WI | 2021-06-08 | 8 | R,Sunitha | 437407452 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Report portal access | Report portal access
63 | BLTM_WI | 2021-04-27 | 50 | R,Sunitha | 435998991 | Pending | Client Validation | CHANGE_CONTROL | 2021-06-14 | 2 | OPPE no show count for Q3 and Q4 2020 | OPPE no show count for Q3 and Q4 2020
64 | BLTM_WI | 2021-04-08 | 69 | R,Sunitha | 436162185 | Scheduled |  | CHANGE_CONTROL | 2021-06-14 | 2 | Create Data Specific report for 271 Eligibility Responses - Ref: 430457768 | Create Data Specific report for 271 Eligibility Responses - Ref: 430457768
65 | CHES_NY | 2021-05-13 | 34 | S N,Harish | 437041415 | Planning In Progress |  | CODING | 2021-06-10 | 6 | CCL reports for Change health project | CCL reports for Change health project
66 | CHES_NY | 2021-06-15 | 1 | S N,Harish | 436706110 | Planning In Progress |  | SCOPING | 2021-06-15 | 1 | ADM ID Label Issue | ADM ID Label Issue
67 | CHES_NY | 2021-05-13 | 34 | J N, Swetha | 436245587 | Draft |  | SCOPING | 2021-06-08 | 8 | Facility Wide Antimicrobial Days of Therapy Report | Facility Wide Antimicrobial Days of Therapy Report
68 | CHES_NY | 2021-05-26 | 21 | Nitish, Sati | 437049183 | Planning In Progress |  | CODING | 2021-06-14 | 2 | Catheter days report is needed for SPS program | Catheter days report is needed for SPS program
69 | CHES_NY | 2021-06-07 | 9 | Nitish, Sati | 437334260 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-16 | 0 | Localize Leapfrog CPOE and BCMA to CHES_NY | Localize Leapfrog CPOE and BCMA to CHES_NY
70 | CHES_NY | 2021-04-08 | 69 | Nitish, Sati | 435962383 | Pending | Client Action Required | SCOPING | 2021-06-14 | 2 | REPORT REQUEST: IPASS Peds residents log | REPORT REQUEST: IPASS Peds residents log
71 | CHLD_DC | 2021-06-11 | 5 | P,Harikrishnan | 437534660 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Modify Denied Days � Detail of Denied Days by Facility and Payer | Modify Denied Days � Detail of Denied Days by Facility and Payer
72 | CHLD_DC | N/A | 0 | P,Harikrishnan | 437625105 | Request For Authorization |  | BACKLOG | N/A | 0 | Create DCHA extract for HIDI | Create DCHA extract for HIDI
73 | CHLD_DC | 2021-05-31 | 16 | P,Harikrishnan | 437295267 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Automate running DRC extracts | Automate running DRC extracts
74 | CHLD_DC | 2021-05-19 | 28 | P,Harikrishnan | 437088210 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-15 | 1 | DoseEdge sending 2 different MRN for same patient. | DoseEdge sending 2 different MRN for same patient.
75 | CHLD_DC | N/A | 0 | P,Harikrishnan | 437625102 | Request For Authorization |  | BACKLOG | N/A | 0 | Create DCHA extract for HIDI | Create DCHA extract for HIDI
76 | CHLD_DC | 2021-05-07 | 40 | P,Harikrishnan | 436905437 | Pending | Client Action Required | SCOPING | 2021-06-15 | 1 | Create new PowerInsight report "Social Work Activity" | Create new PowerInsight report "Social Work Activity"
77 | CHLD_DC | 2021-05-12 | 35 | P,Harikrishnan | 436952823 | Pending | Client Action Required | SCOPING | 2021-06-16 | 0 | Create a new report that will capture RTS: Repeal the shield from the technical comments | Create a new report that will capture RTS: Repeal the shield from the technical comments
78 | CHLD_DC | N/A | 0 | Ravi, Rakesh | 437605842 | Request For Authorization |  | BACKLOG | N/A | 0 | Create DCHA extract for HIDI | Create DCHA extract for HIDI
79 | CHLD_DC | N/A | 0 | Ravi, Rakesh | 437625138 | Request For Authorization |  | BACKLOG | N/A | 0 | Create DCHA extract for HIDI | Create DCHA extract for HIDI
80 | CHLD_DC | 2021-05-25 | 22 | Ravi, Rakesh | 437248852 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-13 | 3 | Create a telehealth report that is used to send data to CTeL | Create a telehealth report that is used to send data to CTeL
81 | CHLD_DC | 2021-05-17 | 30 | Ravi, Rakesh | 437074894 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Create a Payment Monthly Transaction Detail Report | Create a Payment Monthly Transaction Detail Report
82 | CHLD_DC | 2021-06-07 | 9 | Ravi, Rakesh | 437375285 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Modify Summary Report for Behavioral Goal Achievement Report | Modify Summary Report for Behavioral Goal Achievement Report
83 | CHLD_DC | 2021-05-25 | 22 | S, Simant | 437117432 | Scheduled |  | NON_PROD_VALIDATION | 2021-06-14 | 2 | Request to Create Power Plan Report | Request to Create Power Plan Report
84 | CHLD_DC | 2021-05-28 | 19 | S, Simant | 437311303 | Pending | Client Action Required | CODING | 2021-06-14 | 2 | PCPLC Report for Colorectal Program | PCPLC Report for Colorectal Program
85 | CHLD_DC | 2021-03-25 | 83 | S, Simant | 436169422 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Update the existing' %Audit report' to include medicine services and new diagnosis as new criteria. | Update the existing' %Audit report' to include medicine services and new diagnosis as new criteria.
86 | CHLD_DC | 2021-05-12 | 35 | S, Simant | 437027491 | Planning In Progress | Accepted | NON_PROD_VALIDATION | 2021-06-15 | 1 | Kangaroo care report | Kangaroo care report
87 | CHLD_DC | 2021-06-10 | 6 | S, Simant | 437401659 | Planning In Progress |  | CODING | 2021-06-11 | 5 | A report enhancement to give % of Patients with dx order sets based on the admitting dx | A report enhancement to give % of Patients with dx order sets based on the admitting dx
88 | CHLD_DC | 2021-06-10 | 6 | Wagle, Sharvari | 437534722 | Planning In Progress |  | CODING | N/A | 0 | Create a new report for Triage of Asthma and Diabetes patients who are students in the ED | Create a new report for Triage of Asthma and Diabetes patients who are students in the ED
89 | CHLD_DC | 2021-05-24 | 23 | Wagle, Sharvari | 437146465 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-11 | 5 | Modify Discharge Status Change Report to allow users to select date prompts | Modify Discharge Status Change Report to allow users to select date prompts
90 | CHLD_DC | 2021-05-07 | 40 | Wagle, Sharvari | 436905437 | Pending | Client Action Required | SCOPING | 2021-06-15 | 1 | Create new PowerInsight report "Social Work Activity" | Create new PowerInsight report "Social Work Activity"
91 | CHLD_DC | 2021-06-02 | 14 | Wagle, Sharvari | 437364685 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-11 | 5 | Make a copy of the CCL script and update it to pull 90 days of communication + create an Autotext | Make a copy of the CCL script and update it to pull 90 days of communication + create an Autotext
92 | CHLD_DC | 2021-05-06 | 41 | Wagle, Sharvari | 436885302 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | report to look at Arrival by Hour w/ Acuity and a report to look at Acuity Level w. Door to Doc time | report to look at Arrival by Hour w/ Acuity and a report to look at Acuity Level w. Door to Doc time
93 | CHLD_DC | 2021-05-25 | 22 | Wagle, Sharvari | 437248930 | Pending | Client Validation | PROD_VALIDATION | 2021-06-16 | 0 | Update chld_dc_infusion_billing_rpt script with new encounter types | Update chld_dc_infusion_billing_rpt script with new encounter types
94 | CHLD_DC | 2021-06-02 | 14 | Wagle, Sharvari | 437335658 | Pending | Client Validation | PROD_VALIDATION | 2021-06-14 | 2 | Add Patient Portal field to Patient Demo by Appt Report | Add Patient Portal field to Patient Demo by Appt Report
95 | CHLD_DC | 2021-06-11 | 5 | Anushree T | 437446005 | Planning In Progress | Accepted | CODING | 2021-06-15 | 1 | request for custom smart templates | request for custom smart templates
96 | CHLD_DC | 2021-06-10 | 6 | Batheja, Srishti | 437534518 | Planning In Progress |  | SCOPING | 2021-06-15 | 1 | Additional Modifications to the Payment report with Non-AR GL | Additional Modifications to the Payment report with Non-AR GL
97 | CHLD_DC | 2021-06-10 | 6 | Batheja, Srishti | 437480687 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Request List Productivity report showing incorrect date of birth | Request List Productivity report showing incorrect date of birth
98 | CHSI_TN | 2019-07-30 | 687 | Agrawal,Neha | 423106226 | Pending | Client Hold | BACKLOG | 2021-05-17 | 30 | Clinical Application Service Request | Clinical Application Service Request
99 | LCOX_MO | 2021-05-27 | 20 | Gaurav Sinha | 436960406 | Planning In Progress | Accepted | NON_PROD_VALIDATION | 2021-06-10 | 6 | AP - AP TAT reports need the GY cases removed | AP - AP TAT reports need the GY cases removed
100 | LCOX_MO | 2021-05-11 | 36 | Gaurav Sinha | 435310129 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-10 | 6 | New Explorer Menu Report for Med Scanning | New Explorer Menu Report for Med Scanning
101 | LCOX_MO | 2021-05-17 | 30 | Gaurav Sinha | 433459412 | Planning In Progress | Accepted | NON_PROD_VALIDATION | 2021-06-14 | 2 | Custom reporting team | Custom reporting team
102 | LCOX_MO | 2021-05-11 | 36 | Gaurav Sinha | 436814348 | Planning In Progress | Accepted | NON_PROD_VALIDATION | 2021-06-10 | 6 | remove dashes from scripts that use uar_get_code_by displayKEY | remove dashes from scripts that use uar_get_code_by displayKEY
103 | LCOX_MO | 2021-06-15 | 1 | Gaurav Sinha | 437383451 | Planning In Progress |  | SCOPING | 2021-06-15 | 1 | Contact Center Referral Pool report | Contact Center Referral Pool report
104 | LCOX_MO | N/A | 0 | Gangwar,Nidhi | 437395574 | Scheduled For Approval |  | TRIAGE_REVIEW | 2021-06-15 | 1 | remove things from report | remove things from report
105 | LOWE_MA | 2021-05-21 | 26 | Srivastava, Sanjana | 437139280 | Pending | Client Action Required | SCOPING | 2021-06-14 | 2 | CCL - TAT for Lab and ED - stopped working | CCL - TAT for Lab and ED - stopped working
106 | LOWE_MA | 2021-05-26 | 21 | Srivastava, Sanjana | 437171131 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Pre-Procedural COVID Data | Pre-Procedural COVID Data
107 | LOWE_MA | N/A | 0 | Srivastava, Sanjana | 437025608 | Planning In Progress | Accepted | BACKLOG | 2021-06-14 | 2 | Medisolv CMIPPS file and CMOPPS file extracts. | Medisolv CMIPPS file and CMOPPS file extracts.
108 | LOWE_MA | 2021-05-10 | 37 | Srivastava, Sanjana | 436903016 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Error user get with DA2 Observation Reports > See working log for errors | Error user get with DA2 Observation Reports > See working log for errors
109 | LOWE_MA | 2021-05-04 | 43 | Srivastava, Sanjana | 436880874 | Pending | Client Action Required | NON_PROD_VALIDATION | 2021-06-14 | 2 | daily file of scheduling configuration | daily file of scheduling configuration
110 | LOWE_MA | 2021-05-20 | 27 | Srivastava, Sanjana | 436662562 | Planning In Progress |  | BACKLOG | 2021-06-14 | 2 | Report request- antibiotic | Report request- antibiotic
111 | MCH_TX | 2021-05-12 | 35 | Shree,D.Vipula | 436634620 | Pending | Client Action Required | SCOPING | 2021-06-15 | 1 | PHC Grant reports | PHC Grant reports
112 | MCH_TX | 2021-06-02 | 14 | Shree,D.Vipula | 437391312 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-15 | 1 | related to request 436391044 (Telemetry) | related to request 436391044 (Telemetry)
113 | MCH_TX | 2021-04-05 | 72 | Shree,D.Vipula | 436209830 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | Status change from inpatient to OBS after discharge | Status change from inpatient to OBS after discharge
114 | MCH_TX | 2021-04-05 | 72 | Shree,D.Vipula | 436209676 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | CCL report on encounter types inpatient to OBS patients before discharge | CCL report on encounter types inpatient to OBS patients before discharge
115 | MCH_TX | 2021-05-12 | 35 | Srivastava, Sanjana | 436634620 | Pending | Client Action Required | SCOPING | 2021-06-15 | 1 | PHC Grant reports | PHC Grant reports
116 | MCH_TX | 2021-06-02 | 14 | Srivastava, Sanjana | 437391312 | Planning In Progress |  | CHANGE_CONTROL | 2021-06-15 | 1 | related to request 436391044 (Telemetry) | related to request 436391044 (Telemetry)
117 | MCH_TX | 2021-04-26 | 51 | Srivastava, Sanjana | 436685307 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Build new Pain Report | Build new Pain Report
118 | MCH_TX | 2021-04-05 | 72 | Srivastava, Sanjana | 436209830 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | Status change from inpatient to OBS after discharge | Status change from inpatient to OBS after discharge
119 | MCH_TX | 2021-04-05 | 72 | Srivastava, Sanjana | 436209676 | Scheduled |  | PROD_READY | 2021-06-15 | 1 | CCL report on encounter types inpatient to OBS patients before discharge | CCL report on encounter types inpatient to OBS patients before discharge
120 | SANJ_NM | 2021-05-25 | 22 | Nagwekar,Anoop | 436330691 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-11 | 5 | Non-HRSA registered Pharmacy in WAG 340B "1414_flatver4_delta_" files | Non-HRSA registered Pharmacy in WAG 340B "1414_flatver4_delta_" files
121 | SGEN_OH | 2021-03-14 | 94 | Ravi, Rakesh | 433329235 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-15 | 1 | Hospitalist weekly visit report.. | Hospitalist weekly visit report..
122 | SGEN_OH | 2021-04-20 | 57 | Ravi, Rakesh | 436137986 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-13 | 3 | Need daily PowerInsight report of Ventilated Patients. | Need daily PowerInsight report of Ventilated Patients.
123 | SGEN_OH | 2021-03-07 | 101 | Ravi, Rakesh | 435686927 | Pending | Client Validation | CHANGE_CONTROL | 2021-06-15 | 1 | check if the press ganey scripts are pulling correct address details | check if the press ganey scripts are pulling correct address details
124 | SGEN_OH | 2020-12-15 | 183 | Ravi, Rakesh | 434127710 | Pending | Client Validation | CHANGE_CONTROL | 2021-06-15 | 1 | PressGaney reports | PressGaney reports
125 | SGEN_OH | 2021-04-20 | 57 | Anushree T | 436281064 | Planning In Progress |  | NON_PROD_VALIDATION | 2021-06-15 | 1 | Report Request: Blood Transfusion w H&H | Report Request: Blood Transfusion w H&H
126 | SGEN_OH | 2021-02-18 | 118 | Batheja, Srishti | 432963501 | Scheduled |  | PROD_READY | 2021-06-11 | 5 | alert link reports with wrong month and year display | alert link reports with wrong month and year display
127 | SGEN_OH | 2021-04-05 | 72 | Batheja, Srishti | 435750581 | Planning In Progress |  | REVISION | 2021-06-15 | 1 | mamm categories report | mamm categories report
128 | SGEN_OH | 2021-04-15 | 62 | Chandan Sharma | 434541067 | Planning In Progress |  | SCOPING | 2021-06-11 | 5 | Level of Care worklist | Level of Care worklist
129 | SGEN_OH | 2021-06-15 | 1 | Chandan Sharma | 437317203 | Planning In Progress |  | SCOPING | 2021-06-14 | 2 | Humana Flat Files - Supplemental Data Feed Request | Humana Flat Files - Supplemental Data Feed Request
130 | SGEN_OH | 2021-03-24 | 84 | Kumar, Anshuman | 435721222 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Creation of Medical Mutual Payer Flat File Data Feed | Creation of Medical Mutual Payer Flat File Data Feed
131 | SGEN_OH | 2021-04-26 | 51 | Kumar, Anshuman | 435236333 | Pending | Client Validation | NON_PROD_VALIDATION | 2021-06-14 | 2 | Update freetextgoal report | Update freetextgoal report
132 | SGEN_OH | 2021-05-12 | 35 | Kumar, Anshuman | 436974824 | Pending | Client Validation | PROD_READY | 2021-06-14 | 2 | Operational reporting need | Operational reporting need
133 | SGEN_OH | N/A | 0 | Gangwar,Nidhi | 437502998 | Planning In Progress |  | BACKLOG | 2021-06-09 | 7 | Modifications to SGEN_OH_CLINICAL_INTERVENTIONS:DBA report for pharmacy | Modifications to SGEN_OH_CLINICAL_INTERVENTIONS:DBA report for pharmacy
134 | SGEN_OH | N/A | 0 | Gangwar,Nidhi | 437558025 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-14 | 2 | Contaminated urine cultures | Contaminated urine cultures
135 | SGEN_OH | N/A | 0 | Gangwar,Nidhi | 437396642 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-10 | 6 | Need O'Neill Healthcare | Need O'Neill Healthcare
136 | WMMC_MO | 2021-04-20 | 57 | Kumar S,Utham | 436310397 | Planning In Progress |  | CODING | 2021-06-14 | 2 | Report needed for BCBS Flat Files | Report needed for BCBS Flat Files
137 | WMMC_MO | N/A | 0 | Gangwar,Nidhi | 437242246 | Planning In Progress |  | TRIAGE_REVIEW | 2021-06-07 | 9 | Exclude zztest patients on 340B Drug Utilization file. | Exclude zztest patients on 340B Drug Utilization file.